## Project Planner
Thesis Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Week Highlight: | 16 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | WEEKS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Baseline (YOLOv1) implementation | 1 | 3 | 1 | 4 | 100%
Train/test on baseline | 4 | 2 | 4 | 2 | 100%
Adapted (bounding circle) implement | 6 | 3 | 6 | 5 | 66%
Train/test on adaption | 9 | 2 |  |  | 0%
Write Introduction | 1 | 2 | 1 | 4 | 100%
Write Related Works | 1 | 4 | 2 |  | 50%
Write Methods | 3 | 2 |  |  | 0%
Write Results | 12 | 2 |  |  | 0%
Write Conclusion | 14 | 1 |  |  | 0%
Write Discussion | 15 | 2 |  |  | 0%
Make Dataloader for labelme format | 2 | 1 | 6 | 1 | 100%
Make Loss function to measure accuracy | 3 | 1 | 6 | 5 | 66%
Write entrepreneurship (impact) | 16 | 1 |  |  | %
Write abstract | 16 | 1 |  |  | %
Activity 15 | 0 | 0 | 0 | 0 | %
Activity 16 | 0 | 0 | 0 | 0 | %
Activity 17 | 0 | 0 | 0 | 0 | %
Activity 18 | 0 | 0 | 0 | 0 | %
Activity 19 | 0 | 0 | 0 | 0 | %
Activity 20 | 0 | 0 | 0 | 0 | %
Activity 21 | 0 | 0 | 0 | 0 | %
Activity 22 | 0 | 0 | 0 | 0 | %
Activity 23 | 0 | 0 | 0 | 0 | %
Activity 24 | 0 | 0 | 0 | 0 | %
Activity 25 | 0 | 0 | 0 | 0 | %
Activity 26 | 0 | 0 | 0 | 0 | %
[5 empty] | Week number: | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
[6 empty] | Februari |  |  |  | Maart |  |  |  | April |  |  |  |  | Mei |  |  |  | Juni

## Sheet1
2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14
Methods | Methods | Results | Teamweekend |  |  | Teamweekend | Results | Result | Conclusion | Conclusion |  | Hockeywedstrijd | [6 empty] | Hockeywedstrijd | Tentamen |  |  |  | Lustrumdag | Maud's afstudeerfeest | Hockeywedstrijd
[10 empty] | Discussion | Discussion | Entrepreneurship | [13 empty] | Deadline Thesis